## Module List
Back End
Total Modules | We have… | Have to work On…
Login | Login
Dashboard Management | Dashboard Management
User Management | User Management
User Owner Management | User Owner management
Admin Type Management | Admin Type management
Feature Management | Feature Management
Category Management | Category Management
Brand Management | Brand Management
Specification Management | Specification Management
Manufacturer Management | Manufacturer Management
Product Management | Product Management
Batch Management |  | Batch Management
Cart Management |  | Cart Management
Order Management | Order Management
Notification Management | Notification Management
Reports Management | Reports Management
Shipping managements integration Management |  | Shipping managements integration Management
Buyers / Vendor Management |  | Buyers / Vendor Management
Commission Management |  | Commission Management
Tax Management [Based on Product and area] |  | Tax Management [Based on Product and area]
Store creation Management | Store creation Management
Information page builder Management |  | Information page builder Management
FAQ Management | FAQ Management
PDF Management |  | PDF Management
Bulk Upload Management | Bulk Upload Management
Upload Images Management | Upload Images Management
Invoice Management |  | Invoice Management
Inventory Management | Inventory Management
Filter Management | Filter Management
Deals and Offers Management |  | Deals and Offers Management
Rating and Review Management | Rating and Review Management
Front End
Total Modules | We have… | Have to work On…
Login | Login
Registration | Registration
View Products [Category wise] | View Products [Category wise]
View Products [Filter wise] | View Products [Filter wise]
Wish list |  | Wish List
Cart | Cart
Order | Order
Payment Gateway | Payment Gateway
Order History | Order History
User Profile | User Profile
Deals and Offers |  | Deals and Offers
Notification | Notification
Buyer Management |  | Buyer Management
FAQ | FAQ

## First Week
First Week [Back End]
Sr. No. | Date | Module Name | Description | Assign To | Hrs | Days | Status
1 |  | Login | Login for admin panel | Punit
2 |  | Admin Type Mang | CRUD for admin type | Punit
3 |  | User Owner Mang | CRUD for user owner | Punit
4 |  | User Mang | CRUD for admin user | Punit
5 |  | Feature Mang | CRUD for features | Punit
6 |  | Category Mang | CRUD for categorys | Punit
7 |  | Brand Mang | CRUD for brands | Punit
8 |  | Specificatin Mang | CRUD for specificatins | Punit
9 |  | Filter Mang | CRUD for filters | Punit
10 |  | FAQ Management | CRUD for faqs | Punit
11 |  | Information page builder Management | CRUD for informations | Punit
12 |  | Notification Management | Same as Notification Module from MM | Punit
13 |  | Rating and Review Management | Same as PE | Punit
14 |  | Store creation Management | Same as marketing module | Punit
15 |  | Inventory Management | CRUD for inventorys | Satish
16 |  | Product Management | CRUD for products | Prathamesh
17 |  | Bulk Upload Management | CRUD for bulks | Prathamesh
18 |  | Upload Images Management | CRUD for uploads | Prathamesh
19 |  | Dashboard Mang | All respective statics for the different activities | Satish
20 |  | Order Management | Same As PE | Satish
21 |  | Cart Management |  | Satish

## Second Week
Second Week [Back End]
Sr. No. | Date | Module Name | Description | Assign To | Hrs | Days | Status
1 |  | Manufacturer Management |  | Punit
2 |  | Batch Management |  | Ejaz
3 |  | Reports Management |  | Ejaz / Prathamesh / Satish /Punit
4 |  | Shipping managements integration Mang |  | Ejaz
5 |  | Buyers / Vendor Management |  | Ejaz
6 |  | Commission Management |  | Satish
7 |  | Tax Management [Based on Product and area] |  | Satish
8 |  | PDF Management |  | Prathamesh
9 |  | Invoice Management |  | Ejaz
10 |  | Deals and Offers Management |  | Satish

## Third Week
Third Week [Front End]
Sr. No. | Date | Module Name | Description | Assign To | Hrs | Days | Status
1 |  | Login
2 |  | Registration
3 |  | User Profile
4 |  | FAQ
5 |  | Notification
6 |  | Deals and Offers
7 |  | View Products [Category wise]
8 |  | View Products [Filter wise]
9 |  | Wish list
10 |  | Cart
11 |  | Order
12 |  | Order History
13 |  | Payment Gateway
14 |  | Buyer Management

## Fourth Week
Fourth Week Testing and Bugs Solving]
Sr. No. | Date | Module Name | Description | Assign To | Hrs | Days | Status

## Fifth Week
Fifth Week [Testing and bugs solving]
Sr. No. | Date | Module Name | Description | Assign To | Hrs | Days | Status